## Index
SOW Effort-Scoping Calculators — Index
One calculator per product line, all in the same Assumptions → Calculator → Result format. Start with Global Assumptions to set the shared rate, PM %, and timeline multipliers used across every tab below.
Tab | What's included | Go to
GLOBAL
Global Assumptions | Shared blended rate, standard 35% PM rule, short-timeline multipliers, and process reminders referenced by every tab below. | Open tab →
CORE IMPLEMENTATION
Support | Zendesk Support setup — discovery by agent-group tier, business-rule build scaled by count, Guide OOB, action-flow add-ons. | Open tab →
DC | Dynamic Content / localization setup, scaled by # of custom items and # of languages (cascading Low/Mid/High tiers). | Open tab →
Multi Brand | Configuring additional brands within a single Zendesk instance. | Open tab →
Custom HC | ⚠ PLACEHOLDER — Custom Help Center theming/branding, structure, and legacy content migration. No benchmark SOW available yet. | Open tab →
CHANNELS
Voice | Zendesk Talk OOB setup — phone numbers, IVR build by complexity, training/testing. No PM applied. | Open tab →
OOB Messaging | Messaging widget setup (web + other channels like WhatsApp/FB) per brand, plus optional TA guidance. | Open tab →
AI & AUTOMATION
AI Copilot | Two tiers: turning on Copilot features only, or the fuller tier with procedures/config. No PM on the enable-only tier. | Open tab →
AIAA | AI Agents/Advanced Automation — source connection, up to 3 use cases, included API connections, support routing, TA guidance. PM only above 40 hrs. | Open tab →
QUALITY & WORKFORCE
QA | Scorecards, workspaces, AutoQA, Spotlight, calibration/coaching methodology, dashboards, config. No PM applied. | Open tab →
WFM | Workforce Management setup — discovery, config, UAT/training, hypercare, up to 4 workstreams included. | Open tab →
DATA, SECURITY & CUSTOM DEVELOPMENT
Adv Data Privacy | Advanced encryption/BYOK — quick Feature Review, or the full 6-phase KMS implementation. | Open tab →
custom objects | Zendesk Custom Object scope — data model design, build, object-facing UI, migration into objects. | Open tab →
Migration | Ticket/user/org/attachment data migration into Zendesk — mapping, volume, attachments, open-ticket delta handling. | Open tab →
Custom App | Custom Zendesk apps/integrations — sidebar apps, ticket-sidebar widgets, backend integrations (e.g. Envoy Connect). | Open tab →
ANALYTICS & ADD-ONS
Analytics | Explore reporting setup — baseline dashboard/reports/metrics allowance, additional units, optional training session. | Open tab →
Public Slack | 8% modifier on a project's PM + Consultant time for projects that include public Slack channel support. | Open tab →

## Global Assumptions
Global Assumptions & Rules
Shared defaults referenced by every product tab in this workbook. Tabs marked with a green link cell pull their rate directly from here; tabs with their own established rate (custom objects, Migration, Custom App) keep a local rate since those were deliberately set at different levels. Edit values here to update every linked tab at once.
SHARED DEFAULTS
Assumption | Value | Notes / Source
Default blended hourly rate ($) | 258 | Reference rate for any tab that doesn't already have its own established rate. Roughly the midpoint of the three existing calculators' rates ($258 custom objects / $235 Migration / $253 Custom App).
Standard PM % of project hours | 35% | From the original Notes tab: "35% for PM." Applied to total project hours on every tab unless that tab documents an explicit exception (see that tab's Assumptions section).
SHORT-TIMELINE MULTIPLIER (select the delivery timeline on each tab's Result section)
Multiplier — Standard (7+ weeks) | 1 | Baseline, no compression.
Multiplier — 5-7 weeks | 1.2 | From the original Notes tab.
Multiplier — 3-4 weeks | 1.3 | From the original Notes tab.
Multiplier — <3 weeks | 1.4 | From the original Notes tab. Note: will also likely require multiple resources — a timeline this compressed may need a staffing conversation, not just a rate adjustment.
Standalone engagement — KO (0.5h) + design sign-off (0.5h) flat hrs | 1 | Reference only — informational. Applies when a product engagement is sold on its own, not bundled into a Support package: a 30-min kickoff plus a 30-min design sign-off session. Each product tab notes this in its Meeting Cadence section; it is not automatically added to any tab's hours.
PROCESS REMINDERS (apply when assembling the actual SOW document)
• Update the SOW whenever an expected item is not included in scope — don't let an exclusion go unstated.
• The signer needs to initial on any items that are explicitly called out as included, per client sign-off practice.
• "Update weeks of performance" — confirm the period-of-performance language reflects the actual timeline used for the short-timeline multiplier above.
PER-TAB PM EXCEPTIONS (documented overrides to the 35% standard)
Tab | Exception
Voice | No PM needed for this part.
QA | No PM needed for this part.
AIAA | No PM needed if standalone and under 40 total hours; projects over 40 hours should include a PM.
AI Copilot | No PM needed for the "turning on features only" tier.

## Support
Support Implementation Calculator
WHAT'S INCLUDED: Core Zendesk Support setup — discovery by agent-group tier, business-rule (trigger/automation) build scaled by count, optional Guide OOB knowledge base setup, and action-flow add-ons. Groups beyond the first 3 add discovery and configuration effort (see below). Email and forms are the channels covered here; see the Voice and OOB Messaging tabs for those channels.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 3 discovery sessions (Standard tier) / up to 6 (Higher tier), plus up to 2 additional discovery sessions per group beyond 3, per the Discovery hours below.
• Up to 1 collaboration meeting for Knowledge/Help Center (Guide).
• Up to 1 UAT meeting.
• Up to 1 UAT feedback meeting.
• Up to 1 go-live checklist review meeting.
• Up to 1×30-min kickoff (KO).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
DISCOVERY (per agent-group tier)
Discovery hrs — Standard tier (up to 3 discovery sessions, 12 agent teams, 2 agents) | 3 | From the original Support rate card.
Discovery hrs — Higher tier (up to 6 discovery sessions, 22 agent teams, 2 agents) | 6 | From the original Support rate card.
GROUPS BEYOND 3 (additional discovery + configuration effort)
# groups included before additional effort kicks in | 3 | New.
Additional discovery hrs per group beyond 3 (up to 2 meetings) | 2 | New.
Additional configuration/business-rule hrs per group beyond 3 | 3 | New.
BUSINESS RULES (triggers/automations — tiered by count, includes build/testing/hypercare)
Hrs — up to 25 business rules | 15 | ≈0.6 hrs/rule.
Hrs — up to 55 business rules* | 20 | *Includes two action flows. ≈0.36 hrs/rule.
Hrs — up to 85 business rules* | 30 | *Includes two action flows. ≈0.35 hrs/rule.
Hrs — up to 100 business rules (custom) | 35 | Beyond 100, treat as fully custom scoping.
GUIDE / KNOWLEDGE BASE (out-of-the-box)
Guide OOB setup — flat hrs | 10 | Includes new features like Knowledge builder.
ADD-ONS
Additional action flow — hrs each | 4 | Beyond what's included in the Business Rules tier above.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—F)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns G onward calculate automatically.
Scope Name | Discovery Tier | # Groups | # Business Rules | Include Guide OOB? (Y/N) | # Additional Action Flows | Discovery Hrs | Business Rules Hrs | Guide Hrs | Add-on Hrs | Total Hrs | Total Cost ($)
Support Implementation (EXAMPLE — overwrite) | Standard | 3 | 40 | Y | 1 | 3 | 20 | 10 | 4 | 37 | 9546
TOTAL | [5 empty] | 3 | 20 | 10 | 4 | 37 | 9546
SECTION 3 — RESULT
Total hours (pre-PM) | 37
PM hours | 12.95
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 49.95
Final cost ($) | 12887.1
Sources reviewed: original Sow Collab "Support" tab (discovery-by-tier, business-rule tiers, Guide OOB, action-flow add-ons).

## DC
Dynamic Content Calculator
WHAT'S INCLUDED: Localization/translation setup for dynamic content items (macros, triggers, articles, etc.) across one or more languages. Effort tiers cascade: Mid = Low base × 1.5, High = Mid × 1.25 — reflecting the real structure of the original rate card.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
TIER THRESHOLDS (by # of custom items)
Low tier — up to # items | 40 | From the original DC rate card.
Mid tier — up to # items | 85 | From the original DC rate card.
High tier — up to # items | 200 | From the original DC rate card. Beyond this, treat as fully custom scoping.
BASE HOURS (Low tier)
Low tier base hrs — under 5 languages | 10 | From the original DC rate card.
Low tier base hrs — 5+ languages | 20 | From the original DC rate card.
CASCADING MULTIPLIERS
Mid tier multiplier (applied to Low base) | 1.5 | Mid = Low base × this multiplier (10×1.5=15; 20×1.5=30 — matches the original rate card exactly).
High tier multiplier (applied to Mid base) | 1.25 | High = Mid base × this multiplier (15×1.25=18.75; 30×1.25=37.5 — matches the original rate card exactly).
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—C)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns D onward calculate automatically.
Scope Name | # Custom Items | # Languages | Tier (computed) | Base Hrs (Low) | Tier Hrs | — | Total Hrs | Total Cost ($)
Macro Translation (EXAMPLE — overwrite) | 60 | 3 | Mid | 10 | 15 |  | 15 | 3870
TOTAL | 60 | 3 |  |  |  |  | 15 | 3870
SECTION 3 — RESULT
Total hours (pre-PM) | 15
PM hours | 5.25
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 20.25
Final cost ($) | 5224.5
Sources reviewed: original Sow Collab "DC" tab (cascading Low/Mid/High tier multipliers by item count and language count).

## Multi Brand
Multi-Brand Calculator
WHAT'S INCLUDED: Configuring additional brands within a single Zendesk instance. Flat allowance covers up to 3 brands; each brand beyond that is a flat add.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 1hr additional discovery session.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
Flat hrs — included, up to 3 brands | 5 | From the original Multi Brand rate card.
# brands included in the flat allowance | 3 | From the original Multi Brand rate card.
Hrs per additional brand (beyond the included allowance) | 5 | From the original Multi Brand rate card.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—B)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns C onward calculate automatically.
Scope Name | # Total Brands | Additional Brands | — | — | Total Hrs | Total Cost ($)
Multi-Brand Setup (EXAMPLE — overwrite) | 5 | 2 |  |  | 15 | 3870
TOTAL |  |  |  |  | 15 | 3870
SECTION 3 — RESULT
Total hours (pre-PM) | 15
PM hours | 5.25
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 20.25
Final cost ($) | 5224.5
Sources reviewed: original Sow Collab "Multi Brand" tab.

## Custom HC
Custom Help Center Calculator ⚠ PARTIAL PLACEHOLDER
WHAT'S INCLUDED: Custom-themed Help Center (Guide) design/build beyond the out-of-the-box setup already covered on the Support tab — Design and Build/Development are scoped as separate line items, plus category/section structure and legacy content migration. ⚠ Reviewed past Guide SOWs (Everlink SOW 004, the Zimperium proposal, Zendesk Inc./GoFundMe/Gameday Men's Health) for a Design-vs-Build hour split — none itemize hours by phase; they're either fixed-fee totals or phase/round counts without hours. Everlink SOW 004's Guide build was a $6,740 fixed fee (≈27 hrs at $253/hr blended) for a smaller-scope "Guide Updates" engagement — notably less than the 45 hrs (15 Design + 30 Build) below, though scope wasn't identical. Treat the 15/30 split as directional until a matching real SOW is available.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 2×1hr discovery sessions reviewing an existing Figma file (real benchmark: Zendesk Inc. SOW 002, GoFundMe SOW 006).
• Up to 2 rounds of revisions each on Home/Article pages and interior pages, plus a mobile landing/article page.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited — PLACEHOLDER VALUES)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
DESIGN
Design — flat hrs | 10 | PLACEHOLDER — see title note above; no matching past-SOW hour breakdown found. Figma design work, distinct from front-end build.
BUILD / DEVELOPMENT
Build/Development — flat hrs | 25 | PLACEHOLDER — see title note above. HTML/CSS front-end development of the approved design.
STRUCTURE
Hrs per category/section | 0.25 | PLACEHOLDER — no source SOW. Estimate only.
CONTENT MIGRATION
Hrs per 50 legacy articles migrated | 2 | PLACEHOLDER — no source SOW. Estimate only.
MULTI-BRAND HELP CENTER
Additional hrs per brand (beyond first) | 25 | PLACEHOLDER — no source SOW; set equal to the Multi Brand tab's per-brand rate as a starting point.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—D)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns E onward calculate automatically.
Scope Name | # Categories/ Sections | # Legacy Articles to Migrate | # Brands | Design Hrs | Build Hrs | Structure Hrs | Migration Hrs | Total Hrs | Total Cost ($)
Custom Help Center Build (EXAMPLE — overwrite) | 12 | 150 | 1 | 10 | 25 | 3 | 6 | 44 | 11352
TOTAL | 12 | 150 | 1 | 10 | 25 | 3 | 6 | 44 | 11352
SECTION 3 — RESULT
Total hours (pre-PM) | 44
PM hours | 15.4
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 59.4
Final cost ($) | 15325.2
Sources reviewed: ⚠ Design/Build split still uses placeholder hours — reviewed Everlink SOW 004, Zimperium proposal, Zendesk Inc./GoFundMe/Gameday Men's Health, none give a phase-level hour breakdown. Update from a real hour-itemized Custom Help Center SOW as soon as one is available.

## Voice
Voice (OOB) Calculator
WHAT'S INCLUDED: Out-of-the-box Zendesk Talk setup — discovery, phone number configuration, IVR build (scaled by complexity), and training/documentation/testing. Greetings are not recorded as part of this scope. No PM is applied on this tab per the original rate card note.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 1×30-min discovery/setup session per phone line.
• Up to 1×1hr admin training session if this engagement is not bundled with a Support package.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
Discovery — flat hrs | 1.5 | From the original Voice rate card. This is Envoy's effort for the discovery phase — see the meeting cadence note above for how that time is spent.
Hrs per phone number configured | 1.5 | From the original Voice rate card.
Hrs per IVR — Normal complexity | 1 | From the original Voice rate card.
Hrs per IVR — High complexity | 4 | From the original Voice rate card.
Training / documentation / testing — flat hrs | 7 | From the original Voice rate card. This is Envoy's effort for training/doc/testing — see the meeting cadence note above for how that time is spent.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—D)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns E onward calculate automatically. No PM row on this tab — per the original rate card, no PM is needed for Voice OOB setup.
Scope Name | # Phone Numbers | # IVRs | IVR Complexity | Discovery Hrs | Config Hrs | IVR Hrs | Training Hrs | Total Hrs
Voice OOB Setup (EXAMPLE — overwrite) | 2 | 2 | Normal | 1.5 | 3 | 2 | 7 | 13.5
TOTAL | 2 | 2 |  | 1.5 | 3 | 2 | 7 | 13.5
SECTION 3 — RESULT (no PM applied — see note above)
Total hours | 13.5
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. timeline multiplier) | 13.5
Final cost ($) | 3483
Sources reviewed: original Sow Collab "Voice" tab.

## OOB Messaging
OOB Messaging Calculator
WHAT'S INCLUDED: Out-of-the-box messaging widget setup (web messaging widget, plus other channel widgets like WhatsApp/Facebook), per brand. Does not include AIAA (bot) setup — see the AIAA tab for that.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 1×1hr session per widget (messaging + other channel combined).
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
Messaging widget — flat hrs (first widget, per brand) | 6 | From the original OOB Messaging rate card.
Messaging widget — additional hrs (each beyond the first, per brand) | 2 | From the original OOB Messaging rate card.
Other channel widget (WhatsApp/FB, etc.) — flat hrs (first widget, per brand) | 6 | From the original OOB Messaging rate card.
Other channel widget — additional hrs (each beyond the first, per brand) | 2 | From the original OOB Messaging rate card.
TA guidance add-on — flat hrs | 5 | From the original OOB Messaging rate card ("requires a TA: 10 hours").
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—D)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns E onward calculate automatically.
Scope Name | # Messaging Widgets | # Other Channel Widgets | Needs TA Guidance? (Y/N) | — | Widget Hrs | TA Hrs | Total Hrs
Messaging Setup (EXAMPLE — overwrite) | 1 | 1 | N |  | 12 | 0 | 12
TOTAL | 1 | 1 |  |  | 12 | 0 | 12
SECTION 3 — RESULT
Total hours (pre-PM) | 12
PM hours | 4.2
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 16.2
Final cost ($) | 4179.6
Sources reviewed: original Sow Collab "OOB Messaging" tab.

## AI Copilot
AI Copilot Calculator
WHAT'S INCLUDED: Two tiers — simply turning on Copilot features (overview only, no config), or the fuller tier that also builds auto-assist procedures, reviews Copilot recommendations, and configures suggestions. No PM is applied for the "turning on features only" tier per the original rate card.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Tier 1 (Product feature review): up to 1×1.5h session.
• Tier 2 (Expanded effort): up to 1×1hr overview session + up to 2×1hr collaboration sessions.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
Tier 1 — Turning on features & overview — flat hrs | 5 | From the original AI Copilot rate card. No PM needed for this tier.
Tier 2 — Above, plus procedures/best practices/entities/suggestion config — flat hrs TOTAL | 15 | From the original AI Copilot rate card. This is the total for the full tier, inclusive of the Tier-1 work — not additive on top of Tier 1.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—B)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns C onward calculate automatically. PM only applies to Tier 2 — Tier 1 carries no PM per the original rate card.
Scope Name | Tier | — | — | — | Hours | PM Hrs | Total Hrs
AI Copilot Rollout (EXAMPLE — overwrite) | Tier 1 — Enable only |  |  |  | 5 | 0 | 5
TOTAL |  |  |  |  | 5 | 0 | 5
SECTION 3 — RESULT
Total hours (incl. per-row PM) | 5
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. timeline multiplier) | 5
Final cost ($) | 1290
Sources reviewed: original Sow Collab "AI Copilot" tab.

## AIAA
AIAA Calculator
WHAT'S INCLUDED: AI Agents/Advanced Automation setup — source connection & discovery, build of up to 3 standard-size custom use cases (no more than 20 blocks per procedure/dialogue), 2 included API connections/action flows, Zendesk support routing for the messaging channel, and TA guidance time. PM is only needed if the project exceeds 40 total hours or isn't standalone.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 1 session for source connection & initial bot-testing objectives.
• Up to 3×1hr collaboration sessions (including testing discussions).
• Up to 1×1hr admin training session if not bundled with a Support package.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
BASELINE (flat, included in every scope)
Connect sources & discovery (3× 1-hr sessions) — flat hrs | 8 | From the original AIAA rate card. This is Envoy's effort for the connect/discovery phase — see the meeting cadence note above for how that time is spent.
Build up to 3 standard use cases — flat hrs | 8 | From the original AIAA rate card. Standard = no more than 20 blocks per procedure/dialogue.
ZD support routing for messaging channel — flat hrs | 5 | From the original AIAA rate card.
TA time for guidance — flat hrs | 5 | From the original AIAA rate card.
INCLUDED ALLOWANCES
# API connections/action flows included | 2 | From the original AIAA rate card.
# use cases included | 3 | From the original AIAA rate card.
ADD-ONS
Hrs per additional API connection/action flow (beyond included) | 3 | From the original AIAA rate card.
Hrs per additional use case (beyond included) | 3 | From the original AIAA rate card.
PM THRESHOLD
PM-required hour threshold | 40 | No PM needed if standalone and under this many total hours; projects over this threshold should include a PM. From the original AIAA rate card.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—C)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns D onward calculate automatically.
Scope Name | # API Connections/ Action Flows | # Use Cases | Baseline Hrs | Add-on Hrs | PM Hrs | — | Total Hrs
AIAA Rollout (EXAMPLE — overwrite) | 2 | 3 | 26 | 0 | 0 |  | 26
TOTAL | 2 | 3 | 26 | 0 | 0 |  | 26
SECTION 3 — RESULT (PM already applied per-row above the 40-hr threshold)
Total hours (incl. per-row PM) | 26
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. timeline multiplier) | 26
Final cost ($) | 6708
Sources reviewed: original Sow Collab "AIAA" tab.

## QA
QA Calculator
WHAT'S INCLUDED: Up to 2 scorecards (8 rating categories each, plus 5 custom autoscoring categories), 2 workspaces (up to 4 standard roles), AutoQA (up to 6 autoscoring categories, 1 saved dashboard view), up to 2 Spotlight filters, up to 8 agent groups, and calibration/coaching (methodology only — two 30-minute sessions; Envoy does not run live calibration or author coaching content). No PM is applied on this tab per the original rate card.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 4×1hr collaboration sessions.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
BASELINE (flat, included in every scope — sums to 20 hrs)
Discovery — flat hrs | 5 | From the original QA rate card.
Scorecard & rating categories — flat hrs | 1 | From the original QA rate card.
AutoQA — flat hrs | 1 | From the original QA rate card.
Spotlight & review workflows — flat hrs | 1 | From the original QA rate card.
Calibration & coaching — flat hrs | 1 | Methodology only — Envoy does not run live calibration or author coaching content.
Dashboards — flat hrs | 2 | From the original QA rate card.
Config — flat hrs | 4 | From the original QA rate card.
INCLUDED ALLOWANCES
# workspaces included | 2 | From the original QA rate card.
# scorecards included | 2 | From the original QA rate card.
ADD-ONS
Hrs per additional workspace (beyond included) | 1 | From the original QA rate card.
Hrs per additional scorecard, up to 5 rating categories (beyond included) | 1 | From the original QA rate card.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—C)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns D onward calculate automatically.
Scope Name | # Total Workspaces | # Total Scorecards | Baseline Hrs | Add-on Hrs | — | — | Total Hrs
QA Program Setup (EXAMPLE — overwrite) | 2 | 2 | 15 | 0 |  |  | 15
TOTAL | 2 | 2 | 15 | 0 |  |  | 15
SECTION 3 — RESULT (no PM applied — see note above)
Total hours | 15
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. timeline multiplier) | 15
Final cost ($) | 3870
Sources reviewed: original Sow Collab "QA" tab.

## WFM
WFM Calculator
WHAT'S INCLUDED: Workforce Management setup — discovery, configuration, UAT/soft launch/training, and hypercare. Discovery and Config both scale with the number of Agent Teams. Up to 4 workstreams are included; each additional workstream is a flat add-on.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
BASELINE (flat, included in every scope)
Discovery — base flat hrs | 6 | Reconstructed from the original rate card: base 6 hrs + 1.5 hrs per Agent Team. At 1 Agent Team this reproduces the original flat 7.5-hr Discovery figure exactly.
Discovery — hrs per Agent Team | 1.5 | See note above.
Config — base flat hrs | 6 | Reconstructed from the original rate card: base 6 hrs + 1 hr per Agent Team. At 1 Agent Team this reproduces the original flat 7-hr Config figure exactly.
Config — hrs per Agent Team | 1 | See note above.
UAT / soft launch / training — flat hrs | 6 | From the original WFM rate card.
Hypercare — flat hrs | 2 | From the original WFM rate card.
INCLUDED ALLOWANCE
# workstreams included | 4 | From the original WFM rate card.
ADD-ONS
Hrs per additional workstream (beyond included) | 2 | From the original WFM rate card.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—C)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns D onward calculate automatically.
Scope Name | # Total Workstreams | # Agent Teams | Baseline Hrs | Add-on Hrs | — | — | Total Hrs
WFM Rollout (EXAMPLE — overwrite) | 4 | 1 | 22.5 | 0 |  |  | 22.5
TOTAL | 4 | 1 | 22.5 | 0 |  |  | 22.5
SECTION 3 — RESULT
Total hours (pre-PM) | 22.5
PM hours | 7.875
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 30.375
Final cost ($) | 7836.75
Sources reviewed: original Sow Collab "WFM" tab.

## Adv Data Privacy
Advanced Data Privacy Calculator
WHAT'S INCLUDED: Two engagement types — a quick Feature Review (assess ADPP add-on status and readiness only), or the Full Implementation walking through all 6 phases: Discovery & Readiness, Access Request & Portal Setup, KMS Configuration, Sandbox Testing, Production Rollout, and Documentation & Handoff. Client owns their own KMS-side configuration and ongoing key management throughout.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Feature Review: up to 1×1hr additional session.
• Full Implementation: up to 2×1hr discovery sessions, up to 3×1hr configuration guidance sessions, up to 2×1hr testing guidance sessions, up to 1×1hr go-live checklist/approval meeting.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
Feature Review — flat hrs | 2 | Quick assessment only: confirm ADPP add-on is active, review current data/field usage, flag known limitations. From the original Adv Data Privacy rate card.
FULL IMPLEMENTATION — 6 PHASES
Phase 1: Discovery & Readiness — flat hrs | 2 | Confirm KMS provider (AWS/Azure/GCP/Thales), flag known limitations (no key rotation support, possible feature degradation).
Phase 2: Access Request & Portal Setup — flat hrs | 2 | Submit access request in Admin Center, track invitation (expires in 7 days), coordinate with client's KMS owner.
Phase 3: KMS Configuration — hrs (most variable phase; original range 6–10 hrs) | 8 | Guide client through linking their KMS in the Secure Configuration Portal. Client owns actual KMS-side configuration. Editable — set to the midpoint of the original 6–10 hr range.
Phase 4: Sandbox Testing — flat hrs | 6 | Turn on advanced encryption in sandbox, test across affected fields, document degraded functionality, validate with stakeholders.
Phase 5: Production Rollout — hrs (original range 3–5 hrs) | 4 | Enable in production, confirm backfill encrypts correctly, monitor for issues. Editable — set to the midpoint of the original 3–5 hr range.
Phase 6: Documentation & Handoff — hrs (original range 2–3 hrs) | 2.5 | Deliver config/decisions doc; client owns ongoing KMS key management going forward. Editable — set to the midpoint of the original 2–3 hr range.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—B)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns C onward calculate automatically.
Scope Name | Engagement Type | — | — | PM Hrs | — | — | Total Hrs
ADPP Rollout (EXAMPLE — overwrite) | Full Implementation | [5 empty] | 24.5
TOTAL | [6 empty] | 24.5
SECTION 3 — RESULT
Total hours (pre-PM) | 24.5
PM hours | 8.575
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 33.075
Final cost ($) | 8533.35
Sources reviewed: original Sow Collab "Adv Data Privacy" tab (6-phase KMS/encryption rollout process).

## custom objects
Custom Object Effort-Scoping Calculator
WHAT'S INCLUDED: Zendesk Custom Object scope — data model design, build, object-facing UI (sidebar app or admin CRUD UI), and migration of data into the objects. Does NOT cover integrations/middleware — see the Custom App and Migration tabs for those.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 1×1hr meeting per Custom Object.
• Up to 1×1hr meeting for migration collaboration, if relevant.
• Up to 1×1hr meeting for sidebar/app requirements, if needed.
• Up to 1×1hr meeting for sidebar/app training & feedback, if relevant.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited; these drive every calculation below)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
DESIGN PHASE
Design hrs — base per object | 2 | Data type/relationship mapping + signoff workshop time for a single object. Estimate — not derived from an hourly SOW breakdown (past SOWs were fixed-bid).
Design hrs — per field | 0.15 | Incremental design/validation time per field. Estimate.
Design hrs — per relationship field | 1 | Relationship fields need cross-object mapping + validation, so weighted higher than flat fields. Estimate.
BUILD PHASE
Build hrs — base per object | 3 | Object shell creation and configuration. Estimate.
Build hrs — per field | 0.25 | Field creation + basic validation. Estimate, informed by Everlink's 21–200 column objects.
Build hrs — per relationship field | 2 | Relationship fields require build + cross-object testing. Estimate.
MIGRATION (only applied if Migration Needed = Y)
Migration hrs — flat per object | 8 | Field mapping (legacy schema → CO schema) + CSV import + spot-check, per object. Modeled loosely on Everlink's Cherwell→CO migration. Estimate.
UI / APP LAYER
UI hrs — None: base | 0 | No object-facing app in scope.
UI hrs — None: per screen | 0
UI hrs — Read-only sidebar: base | 24 | Ticket sidebar app, read-only lookup/display. Modeled loosely on Assurity/Everlink sidebar apps. Estimate.
UI hrs — Read-only sidebar: per screen | 6 | Additional panel/view beyond the first. Estimate.
UI hrs — Admin CRUD UI: base | 40 | Standalone create/update/delete admin UI (e.g. Everlink's NavBar app). Estimate.
UI hrs — Admin CRUD UI: per screen | 10 | Additional list/detail screen. Estimate.
OVERHEAD
QA % of Design+Build+UI hours | 15% | Object/relationship validation + UI testing. Estimate.
Docs & training — flat hrs per project | 4 | Data model doc + admin/agent training. Flat regardless of object count.
SECTION 2 — CALCULATOR (add one row per custom object; only edit columns A–F)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns G onward calculate automatically.
Object Name | # Fields | # Relationship Fields | Migration Needed? (Y/N) | UI Type | # UI Screens | Design Hours | Build Hours | Migration Hours | UI Hours | QA Hours | Docs Hours | Total Hours | Total Cost ($)
Client Lookup Object (EXAMPLE — overwrite) | 30 | 2 | N | Read-only sidebar | 1 | 8.5 | 14.5 | 0 | 30 | 7.95 | 0.2 | 61.15 | 15776.7
TOTAL | 30 | 2 |  |  |  | 8.5 | 14.5 | 0 | 30 | 7.95 | 0.2 | 61.15 | 15776.7
# Objects entered | 1
SECTION 3 — RESULT
Suggested effort band | Mid | Bands: Low = 1 object/<25 fields/no relationships. Mid ≈ Assurity precedent. High ≈ Everlink precedent.
Total estimated hours / cost (pre-PM) | 61.15 | 15776.7
PM hours (35% standard) | 21.4025
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 82.5525
Final cost ($, incl. PM + timeline) | 21298.545
Sources reviewed: Assurity Custom App Build SOW, Everlink Payment Services SOW 003.

## Migration
Ticket Migration Effort-Scoping Calculator
WHAT'S INCLUDED: Ticket/user/org/attachment data migration into Zendesk — data mapping, ticket-volume build/import/testing, attachment handling, and open/non-closed ticket delta handling. NOT ongoing integrations or custom object build — see those tabs for that scope.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 1×1.5hr data-mapping session.
• Up to 1×1hr sample ticket feedback session.
• Up to 1×1hr close ticket feedback session.
• Up to 1×1hr go-live readiness collaboration session.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited; these drive every calculation below)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
PROJECT-LEVEL (applied once per project, split evenly across the rows you enter)
Kickoff, mapping workbook, sample validation & cutover coordination — flat hrs per project | 8 | Reflects the standard Data Migration Workbook flow. This is Envoy's effort for this phase — see the meeting cadence note above for how that time is spent.
DATA MAPPING
Mapping/dev hrs — up to 10 custom fields | 2 | Flat, covers both the data-mapping session and developer implementation time combined.
Mapping/dev hrs — 10–30 custom fields (subtotal, not additive on top of the tier above) | 4 | Flat subtotal for this tier — covers both mapping and developer time.
Mapping/dev hrs — additional per grouping of 20 fields beyond 30 | 4 | Added on top of the 10–30 tier's 6 hrs for every additional 20 fields (or part thereof) beyond 30. Covers both mapping and developer time.
TICKET VOLUME
Build/import/testing hrs — per 1,000 tickets | 0.2 | Derived from a real SFDC migration quote; migrations are batch/API-driven so this mainly captures validation and failure remediation effort.
ATTACHMENTS
Handling/testing hrs — per 1,000 attachments | 0.15 | Attachment volume slows migration throughput and adds validation surface (CLEAR precedent).
OPEN / NON-CLOSED TICKETS (delta migration)
Open-ticket threshold for manual vs. automation approach | 200 | Per Envoy's Data Migration Workbook.
Manual approach — flat hrs (used when open tickets ≤ threshold) | 3 | Build a view + macro to notify requesters.
Automation approach — base hrs (used when open tickets > threshold) | 4 | Build the requester-notification automation + warning triggers before cutover.
Automation approach — additional hrs per 1,000 open tickets | 1.5 | Each additional automation cycle needs its own pass.
SOURCE SYSTEM COMPLEXITY MULTIPLIER (applied to mapping + volume + attachment + open-ticket hours)
Multiplier — CSV export | 0.75 | Most common source format.
Multiplier — API pull | 1 | Auth/rate-limit handling and incremental pulls.
Multiplier — CRM (Salesforce / other) | 1 | "SFDC is always tricky" — object relationships and record-type mapping add real overhead.
MIGRATION METHOD OVERHEAD (flat, applied once per row)
Flat overhead hrs — Custom developer (e.g. internal dev) | 0 | Variable cost already captured above.
Flat overhead hrs — Migration tool (e.g. Relokia) | 10 | Tool setup/config + EM time bundled here as a flat add.
OVERHEAD
QA/validation % of mapping + volume + attachment + open-ticket hours | 15% | Structured sample-migration validation, modeled on the CLEAR Sample Migration Validation Guide.
SECTION 2 — CALCULATOR (add one row per migration scope; only edit columns A–G)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns H onward calculate automatically.
Migration Scope Name | # Tickets | # Attachments | # Custom Fields | # Open/Non- Closed Tickets | Source System | Migration Method | Mapping Hrs | Volume Hrs | Attachment Hrs | Open-Ticket Hrs | QA Hrs | Total Hrs | Total Cost ($)
Closed Tickets (EXAMPLE — overwrite) | 120000 |  | 20 | 260 | API pull | Custom developer | 4 | 24 | 0 | 5.5 | 5.025 | 39.0583 | 10077.05
TOTAL | 120000 | 0 | 20 | 260 |  |  | 4 | 24 | 0 | 5.5 | 5.025 | 39.0583 | 10077.05
# Migration scopes entered | 1
SECTION 3 — RESULT
Suggested effort band | Mid | Bands by total ticket volume: Low <25k. Mid 25k–150k. High >150k.
Total estimated hours / cost (pre-PM) | 39.0583 | 10077.05
PM hours (35% standard) | 13.6704
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 52.7287
Final cost ($, incl. PM + timeline) | 13604.0175
Sources reviewed: Envoy Data Migration Workbooks, CLEAR Sample Migration Validation Guide, AMI Strategies / Dye & Durham / SFDC migration scoping threads.

## Custom App
Custom App Effort-Scoping Calculator
WHAT'S INCLUDED: Custom Zendesk apps/integrations — sidebar apps, ticket-sidebar widgets, and backend integrations (e.g. Envoy Connect). NOT custom objects or data migration — see those tabs for that scope.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 1×1.5hr requirements session.
• Up to 2×1hr feedback sessions.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited; these drive every calculation below)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
PROJECT-LEVEL (kickoff + post-launch/transition, applied once per project, split evenly across rows entered)
Kickoff + post-launch/transition — flat hrs per project | 10 | Anchored to State Bar of California SOW 004 Phase 1 (Kickoff) and Phase 6 (Post-Go-Live/Transition).
DESIGN PHASE
Design hrs — base per app | 9 | Calibrated against State Bar SOW 004 Phase 2 (Architecture & Design).
Design hrs — per field/data point | 0.5 | Field-by-field mapping and TDD documentation.
Design hrs — per field option (dropdown value) | 0.1 | Calibrated to the SOW 004 base case (30 field options).
Design hrs — flat add if attachment sync is in scope | 6 | Attachment sync between systems adds real design surface.
BUILD PHASE
Build hrs — base per app | 6 | Calibrated against State Bar SOW 004 Phase 3 (Build), the largest single phase.
Build hrs — per field/data point | 0.66 | Calibrated to the SOW 004 base case.
Build hrs — per field option (dropdown value) | 0.15 | Calibrated to the SOW 004 base case.
Build hrs — flat add if attachment sync is in scope | 8 | Attachment sync build/testing overhead.
EXTERNAL THIRD-PARTY API MULTIPLIER (applied to Design + Build + QA hours)
Multiplier — calls an external 3rd-party API (e.g. translation, CRM) | 1.3 | TransPerfect's translation sidebar app ran an 8–10 week timeline vs. State Bar's 4–6 weeks for a simpler sync.
APP TYPE MULTIPLIER (applied to Design + Build hours)
Multiplier — Read-only sidebar app (display only) | 0.75 | Simplest profile — Assurity's read-only sidebar app.
Multiplier — Sidebar app with write-back actions | 1 | Baseline.
Multiplier — Backend integration (e.g. Envoy Connect, no UI) | 1 | Baseline — the State Bar of California SOW 004 profile itself.
Multiplier — Combined sidebar UI + backend integration | 1.3 | Everlink's combined sidebar-lookup + full NavBar CRUD UI + backend sync — the largest app-layer scope reviewed.
QA / GO-LIVE PHASE
QA hrs — base per app | 7 | Calibrated against State Bar SOW 004 Phase 4 (QA & Go-Live Prep).
QA hrs — per field/data point | 0.2 | Calibrated to the SOW 004 base case.
QA hrs — flat add if attachment sync is in scope | 2 | Calibrated to the SOW 004 base case.
TRAINING
Training hrs — flat per app | 5 | Matches State Bar SOW 004 Phase 5 (Training) exactly.
SECTION 2 — CALCULATOR (add one row per app/integration; only edit columns A–F)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns G onward calculate automatically.
App Name | # Fields / Data Points | # Field Options | Attachment Sync? (Y/N) | Calls External API? (Y/N) | App Type | Design Hrs | Build Hrs | QA Hrs | Training Hrs | Total Hrs | Total Cost ($)
Jira Sync Integration (EXAMPLE — overwrite) | 20 | 30 | N | N | Read-only sidebar app (display only) | 16.5 | 17.775 | 11 | 5 | 50.9417 | 13142.95
TOTAL | 20 | 30 |  |  |  | 16.5 | 17.775 | 11 | 5 | 50.9417 | 13142.95
# Apps entered | 1
SECTION 3 — RESULT
Suggested effort band | Low | Bands by total hours: Low <60. Mid 60–120 (≈ State Bar SOW 004). High >120 (≈ Everlink / TransPerfect).
Total estimated hours / cost (pre-PM) | 50.9417 | 13142.95
PM hours (35% standard) | 17.8296
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 68.7712
Final cost ($, incl. PM + timeline) | 17742.9825
Sources reviewed: The State Bar of California SOW 004 (v4), TransPerfect Custom Zendesk App SOW 001 (v2), Assurity Custom App Build SOW 001, Everlink Payment Services SOW 003.

## Analytics
Analytics (Explore) Calculator
WHAT'S INCLUDED: Baseline Explore reporting setup — up to 1 dashboard, 5 reports, and 3 custom metrics/attributes, plus an overview meeting. Anything beyond the baseline is scoped as additional units below, plus an optional report-building training session and a single report-requirements review meeting (counted as real hours in the calculator below, not just informational).
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• Up to 1×30-min kickoff call.
• Up to 1 discovery & requirements session (business process review, goals, and report/dashboard requirements).
• Up to 2×1hr sessions to build and review the functional report design.
• Up to 2 rounds of client review & feedback on the configuration.
• Up to 1×60-min training & handoff session for Admins & Agents.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
BASELINE (minimum 10 hrs — up to 1 dashboard, 5 reports, 3 custom metrics/attributes; includes overview meeting)
Baseline — flat hrs | 10 | From the original Analytics rate card.
ADDITIONAL UNITS (beyond baseline)
Hrs per additional dashboard | 2.5 | From the original Analytics rate card.
Hrs per additional custom report | 1.5 | From the original Analytics rate card.
Hrs per additional custom metric/attribute | 2 | From the original Analytics rate card.
OPTIONAL ADD-ON
Report-building training session — flat hrs | 2 | 1-hour training session. From the original Analytics rate card.
REQUIREMENTS REVIEW
Report requirements review meeting — flat hrs (1×1hr, once per scope) | 1 | Single meeting to review report requirements, per your direction — not scaled by hours.
SECTION 2 — CALCULATOR (add one row per scope; only edit columns A—E)
Row below marked EXAMPLE is a sample entry — overwrite it. Columns F onward calculate automatically. Enter TOTAL counts (baseline is netted out automatically) for dashboards/reports/metrics.
Scope Name | # Total Dashboards | # Total Reports | # Total Custom Metrics | Include Training Session? (Y/N) | Baseline+ Addl Hrs | Requirements Meeting Hrs | Total Hrs
Explore Setup (EXAMPLE — overwrite) | 1 | 5 | 3 | N | 10 | 1 | 11
TOTAL |  |  |  |  | 10 |  | 11
SECTION 3 — RESULT
Total hours (pre-PM) | 11
PM hours | 3.85
Project timeline (select) | Standard (7+ weeks)
Final hours (incl. PM + timeline multiplier) | 14.85
Final cost ($) | 3831.3
Sources reviewed: original Sow Collab "Analytics" tab.

## Public Slack
Public Slack Community Support Calculator
WHAT'S INCLUDED: A modifier for projects that include a shared/public Slack channel for client support alongside the main engagement. The original rate card defines this as a flat 8% add-on to that project's PM + Consultant time, rather than a standalone build — so this tab is a modifier calculator, not a line-item calculator like the others.
MEETING CADENCE (informational — already reflected in the effort hours below; not additive)
• This is always an add-on to another project's hours, not a standalone sale — the standard note below is included for consistency but is unlikely to apply in practice.
• If this engagement is standalone (not bundled with a Support package): +30-min kickoff, +30-min design sign-off (see Global Assumptions).
SECTION 1 — ASSUMPTIONS (gray = calibrated reference values, not meant to be edited)
Assumption | Value | Notes / Source
Blended hourly rate ($) | 258 | Linked to Global Assumptions default rate.
Public Slack support — % of project PM + Consultant time | 8% | From the original Public Slack rate card.
SECTION 2 — CALCULATOR (enter the project's total PM + Consultant hours from its own tab)
Row below marked EXAMPLE is a sample entry — overwrite it. Column C onward calculates automatically.
Project Name | Project PM + Consultant Hrs | Public Slack Hrs (8%) | — | Total Hrs | Total Cost ($)
Client Rollout (EXAMPLE — overwrite) | 120 | 9.6 |  | 9.6 | 2476.8
TOTAL |  | 9.6 |  | 9.6 | 2476.8
SECTION 3 — RESULT (this is already a % modifier — no additional PM or timeline multiplier applies)
Total Public Slack hours / cost | 9.6 | 2476.8
Sources reviewed: original Sow Collab "Public Slack" tab.